## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Tanmayi | 2025-11-03 | OCR not extracting full address | Sprint 1 | Backend | Functional | Improved preprocessing | 2025-11-04 | Closed | Verified
2 | Teja | 2025-11-13 | Inconsistent address scores | Sprint 2 | Backend | Algorithmic | Adjusted threshold & retrained | 2025-11-14 | Closed | Improved
3 | Tanmayi | 2025-11-21 | Frontend not showing fraud outputs | Sprint 2 | Frontend | UI | Fixed JSON parsing | 2025-11-22 | Closed | Verified
4 | Teja | 2025-11-24 | GNN producing NaN values | Sprint 2 | Backend | Model | Normalized data | 2025-11-25 | Closed | Stable
5 | Tanmayi | 2025-11-27 | AML duplicate detection failing | Sprint 3 | Backend | Logic | Added hashing | 2025-11-30 | Closed | Working
6 | Teja | 2025-11-30 | Invalid file formats upload | Sprint 3 | Frontend | UI | Added MIME validation | 2025-12-03 | Closed | Success
7 | Tanmayi | 2025-12-02 | Pipeline slow | Sprint 3 | Backend | Performance | Added async + caching | 2025-12-05 | Closed | 35% faster
8 | Teja | 2025-11-04 | Dashboard graphs not updating | Sprint 4 | Frontend | Integration | Re-linked data binding | 2025-12-07 | Closed | Works
9 | Tanmayi | 2025-12-06 | Fraud alerts missing | Sprint 4 | Backend | Functional | Fixed alert trigger | 2025-12-08 | Closed | Correct
10 | Teja | 2025-12-08 | UI alignment issues | Sprint 4 | Frontend | UI | Adjusted CSS | 2025-12-09 | Closed | Final

## Sheet2
Logical
User Interface
Maintainability
Standards
Others